## Bid Overview and Team
[CRM Number]
[Client and Opportunity] | Al Noor Credit Bureau (ANCB) - Creative Awareness Campaign for Financial Literacy
Bid Overview and Team
Location |  | Technical Lead
Legal Entity |  | Bid Manager
Estimated Contract Value | AED 450,000
Governance Level Required
Tender Validity
Confirmation of Intent to Bid
Site Visit/Client Meeting (if applicable)
Client Point of Contact
Tender Queries Deadline
Tender Query Recipient and Details
Submission Deadline | 15 July 2025, 4:00 PM (UAE Time)
Submission Requirements
Submission Format? Hard Copies / Portal / Email
If Hard Copy, Specify Details of Submission
Delivery Address
Additional Notes/Requirements
Bid Strategy
Bid Strategy
Client Pillars
Win Themes / USPs:

## Bid Deliverables
[CRM Number]
Al Noor Credit Bureau (ANCB) - Creative Awareness Campaign for Financial Literacy
Bid Deliverables
Technical Bid | [14 empty] | Input required from?
Client Ref from RFP | Section Heading | Sub-Section Heading | Deliverable Requirement | Evaluation Criteria | Client Format? Letterhead? Table? | Page/ Word Limit | Owner | Status | Comments | Pink Reviewer | Pink Review Complete? | Red Reviewer | Red Review Complete? | Final Page Turner Complete? |  | Compilation Status | Ready for Submission?
[10 empty] | Due Date: | Due Date: | Due Date: | Due Date: | Due Date:
| Cover Letter and Executive Summary |  | • Provide a formal letter of transmittal signed by an authorized representative. • Include a concise, high-level summary of the proposed solution, highlighting the unique creative concept and expected campaign impact. • Clearly state the agency's understanding of ANCB's mission regarding financial literacy. | • Professionalism and clarity of communication. • Immediate demonstration of understanding and strategic alignment. |  |  | Granite MENA
| Agency Profile and Relevant Experience |  | • Provide a comprehensive company profile, including legal structure, size, and core competencies. • Detail a minimum of three case studies demonstrating successful, integrated awareness campaigns, preferably within the financial services sector or government/regulatory environment. • Clearly articulate how the agency's experience meets the 25% evaluation criteria for relevance. | • Depth and breadth of relevant experience (25%). • Proven track record in managing nationwide campaigns and media buying. • Stability and capacity of the agency. |  |  | Granite MENA
| Strategic Creative Approach and Messaging Framework |  | • Present the overarching campaign strategy deck, detailing the proposed approach to target individuals and SMEs. • Define the core creative concept and rationale that will drive the 35% Creativity score. • Develop the key messaging framework, ensuring clarity, cultural sensitivity, and alignment with responsible borrowing principles. • Detail the proposed media mix strategy (digital, print, outdoor) optimized for UAE resident reach. | • Originality and impact of the creative concept (35%). • Strategic soundness of the messaging framework. • Demonstrated understanding of financial literacy communication challenges. |  |  | Garreth Amoore
| Creative Asset Production Plan |  | • Provide mock-ups or conceptual sketches for the required deliverables (10+ digital creatives, 3 outdoor billboard designs). • Detail the production workflow for video and rich media assets. • Outline the quality assurance process for all creative outputs to ensure brand consistency and compliance. | • Quality and feasibility of proposed creative assets. • Efficiency of the production timeline. |  |  | MetaMinds Studio
| Project Team Structure and Expertise |  | • Provide an organizational chart showing the dedicated project team, including roles (e.g., Creative Director, Media Planner, Account Manager). • Include CVs and profiles for key personnel, highlighting specific experience in financial sector campaigns. • Clearly define the roles and responsibilities of the ANCB liaison and the agency's primary contact. | • Qualifications and relevant experience of the proposed team (15%). • Stability and availability of key personnel. |  |  | Granite MENA
| Project Methodology, Media Management, and Reporting |  | • Detail the methodology for media planning, buying, and performance tracking across all channels. • Describe the tools and metrics used to track campaign effectiveness (KPIs). • Commit to providing monthly progress and performance reports, including actionable insights and optimization recommendations. • Provide the post-campaign report structure and content commitment. | • Robustness of performance tracking and reporting methodology. • Clarity of media management approach. |  |  | Siren Search
Commercial Bid
Client Ref | Section Heading | Sub-Section Heading | Deliverable Requirement | Evaluation Criteria |  | Page/ Word Limit | Owner | Status | Comments | Pink Reviewer | Pink Review Complete? | Red Reviewer | Red Review Complete? | Final Page Turner Complete? |  | Compilation Status | Ready for Submission?
[10 empty] | Due Date: | Due Date: | Due Date: | Due Date: | Due Date:
| Investment Proposal and Cost Breakdown |  | • Provide a detailed cost breakdown itemizing fees for strategy, creative development, asset production, media planning/management, and reporting. • Ensure the total proposed cost is competitive and within the estimated AED 450,000 budget. • Clearly define payment milestones tied to specific deliverables (e.g., Strategy Approval, Asset Delivery, Post-Campaign Report). • List all assumptions made in formulating the cost proposal (e.g., media budget exclusion, third-party costs). | • Cost competitiveness and value for money (15%). • Transparency and clarity of the cost breakdown. • Alignment of payment milestones with ANCB approval points. |  |  | Granite MENA
| Delivery Timeline and Project Schedule |  | • Provide a comprehensive, phased project timeline from contract award to final post-campaign report submission. • Highlight critical path items and key ANCB review/approval points. • Demonstrate the feasibility of the proposed schedule to meet the 10% evaluation criteria for delivery timeline. | • Realism and efficiency of the proposed timeline (10%). • Clear identification of milestones and dependencies. |  |  | Granite MENA
| Mandatory Forms and Declarations |  | • Provide a signed confidentiality declaration as required by ANCB. • Acknowledge and accept ANCB's terms regarding ownership of all developed materials. • Provide necessary legal and financial documentation (e.g., trade license, VAT registration). | • Compliance with mandatory submission requirements. |  |  | Granite MENA

## Timeline
[CRM Number]
[Client and Opportunity]
Bid Timeline
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
|  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Item | Description | Owner | Date | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09
Internal and Governance
1 | Qualification/Bid No Bid Approval Call
2 | Bid Strategy/Win Lab Session
3 | TQ Deadline
4 | Proposal Completed
5 | Proposal Submission Approval Call
6 | Proposal Submission to Client
Mandatory Sign-offs
7 | Commercial and Legal Review
8 | Pricing Review
Proposal Development
9 | Kick-off Meeting
10 | First Drafts
11 | 1st Review/ Pink Review
12 | Second Drafts
13 | 2nd Review/ Red Review
14 | Final Drafts
15 | Pricing/Fee Strategy Development and Review
16 | Final Formatting
17 | Final Page Turner Review
Internal Milestone
18 | Sub/Partner Fees Received
19 | Internal Pricing Complete
20 | Internal Pricing Review
21 | External Client Pricing Model Complete
22 | Identify and Log Key Risks
23 | Identify Key Assumptions, Exclusions and Deviations
Team Leave (During Bid)
1 | [Name]

## hiddenSheet (hidden)
gfi_affaireegis:54DXkNRPQbYFQQ0srjcPZdsLa0R9Aknr5PDymOu6K4xC67aH8LE/flo5iWgEJSLHpXD6StjFoYnxccoVsDSY/A==:gfi_affaireegisid=%28Do%20Not%20Modify%29%20Project&checksumLogicalName=%28Do%20Not%20Modify%29%20Row%20Checksum&modifiedon=%28Do%20Not%20Modify%29%20Modified%20On&gfi_number=No.&gfi_name=Name&gfi_description=Description&gfi_geography=Geography&gfi_directaccountid=Direct%20Client&gfi_finalclientid=End%20Client&gfi_subsidiary=Organization&gfi_responsable_oppotunity=Project%20manager&statuscode=Status%20Reason&gfi_gonogo=Go%2fNo%20Go&gfi_totalamount=Amount%20%28cur.%29&gfi_offersubmission=Proposal%20submission%20date&gfi_scheduledattribution=Date%20estimated%20signature&createdon=Created%20On&createdby=Created%20By
01. Lead | 04. Opportunity | 05. Application under preparation | 06. Application under evaluation | 09. Proposal under preparation | 10. Proposal under evaluation | 11. Proposal won (not signed) | 12. Proposal signed | 02. Abandoned by Egis | 03. Abandoned by Client | 07. No Go | 08. Application rejected | 13. Project closing | 14. Abandoned by client (post-submission) | 15. No Bid | 16. Lost proposal | 17. Revised | 18. Error
Go | No Go